## Project Tracker
Project Summary
Total Tasks:
Completed:
In Progress:
Blocked:
Completion %:
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | %Complete
T001 | Project Kickoff | JD | 2026-07-01 | 2026-07-01 |  | Completed | High | 100%
T002 | Requirements Gathering | AS | 2026-07-01 | 2026-07-10 |  | Completed | High | 100%
T003 | System Architecture Design | JD | 2026-07-05 | 2026-07-15 |  | Completed | High | 100%
T004 | UI/UX Wireframes | MK | 2026-07-08 | 2026-07-20 |  | Completed | Medium | 100%
T005 | Database Schema Design | JD | 2026-07-12 | 2026-07-22 |  | Completed | High | 100%
T006 | API Development | RW | 2026-07-18 | 2026-08-05 |  | In Progress | High | 65%
T007 | Frontend Development | MK | 2026-07-22 | 2026-08-15 |  | In Progress | High | 40%
T008 | Backend Logic Module | RW | 2026-07-25 | 2026-08-10 |  | In Progress | High | 50%
T009 | Testing - Unit | AS | 2026-08-01 | 2026-08-12 |  | Not Started | Medium | 0%
T010 | Testing - Integration | AS | 2026-08-10 | 2026-08-25 |  | Not Started | Medium | 0%
T011 | User Acceptance Testing | AS | 2026-08-22 | 2026-09-05 |  | Not Started | High | 0%
T012 | Documentation | JD | 2026-08-01 | 2026-08-20 |  | Blocked | Medium | 15%
T013 | Security Audit | RW | 2026-08-15 | 2026-08-30 |  | Not Started | High | 0%
T014 | Performance Optimization | RW | 2026-08-20 | 2026-09-05 |  | Not Started | Low | 0%
T015 | Deployment Preparation | JD | 2026-08-25 | 2026-09-01 |  | Not Started | High | 0%
T016 | Production Deployment | JD | 2026-09-01 | 2026-09-03 |  | Not Started | High | 0%
T017 | Post-Launch Monitoring | MK | 2026-09-03 | 2026-09-10 |  | Not Started | High | 0%
T018 | Stakeholder Review | AS | 2026-09-05 | 2026-09-08 |  | Not Started | Medium | 0%
T019 | Final Report | JD | 2026-09-08 | 2026-09-12 |  | Not Started | Medium | 0%
T020 | Project Closure | JD | 2026-09-12 | 2026-09-12 |  | Not Started | High | 0%

## Gantt Chart
Task ID | Task Name | Start | End | Status | Jul 01 | Jul 02 | Jul 03 | Jul 04 | Jul 05 | Jul 06 | Jul 07 | Jul 08 | Jul 09 | Jul 10 | Jul 11 | Jul 12 | Jul 13 | Jul 14 | Jul 15 | Jul 16 | Jul 17 | Jul 18 | Jul 19 | Jul 20 | Jul 21 | Jul 22 | Jul 23 | Jul 24 | Jul 25 | Jul 26 | Jul 27 | Jul 28 | Jul 29 | Jul 30 | Jul 31 | Aug 01 | Aug 02 | Aug 03 | Aug 04 | Aug 05 | Aug 06 | Aug 07 | Aug 08 | Aug 09 | Aug 10 | Aug 11 | Aug 12 | Aug 13 | Aug 14 | Aug 15 | Aug 16 | Aug 17 | Aug 18 | Aug 19 | Aug 20 | Aug 21 | Aug 22 | Aug 23 | Aug 24 | Aug 25 | Aug 26 | Aug 27 | Aug 28 | Aug 29 | Aug 30 | Aug 31 | Sep 01 | Sep 02 | Sep 03 | Sep 04 | Sep 05 | Sep 06 | Sep 07 | Sep 08 | Sep 09 | Sep 10 | Sep 11 | Sep 12 | Sep 13 | Sep 14 | Sep 15
T001 | Project Kickoff | 2026-07-01 | 2026-07-01 | Completed
T002 | Requirements Gathering | 2026-07-01 | 2026-07-10 | Completed
T003 | System Architecture Design | 2026-07-05 | 2026-07-15 | Completed
T004 | UI/UX Wireframes | 2026-07-08 | 2026-07-20 | Completed
T005 | Database Schema Design | 2026-07-12 | 2026-07-22 | Completed
T006 | API Development | 2026-07-18 | 2026-08-05 | In Progress
T007 | Frontend Development | 2026-07-22 | 2026-08-15 | In Progress
T008 | Backend Logic Module | 2026-07-25 | 2026-08-10 | In Progress
T009 | Testing - Unit | 2026-08-01 | 2026-08-12 | Not Started
T010 | Testing - Integration | 2026-08-10 | 2026-08-25 | Not Started
T011 | User Acceptance Testing | 2026-08-22 | 2026-09-05 | Not Started
T012 | Documentation | 2026-08-01 | 2026-08-20 | Blocked
T013 | Security Audit | 2026-08-15 | 2026-08-30 | Not Started
T014 | Performance Optimization | 2026-08-20 | 2026-09-05 | Not Started
T015 | Deployment Preparation | 2026-08-25 | 2026-09-01 | Not Started
T016 | Production Deployment | 2026-09-01 | 2026-09-03 | Not Started
T017 | Post-Launch Monitoring | 2026-09-03 | 2026-09-10 | Not Started
T018 | Stakeholder Review | 2026-09-05 | 2026-09-08 | Not Started
T019 | Final Report | 2026-09-08 | 2026-09-12 | Not Started
T020 | Project Closure | 2026-09-12 | 2026-09-12 | Not Started